## Slide 1
UNCLASSIFIED
MAVEN BUILDER TRAINING — FORCE ROLLOUT PLAN
USAREUR-AF Operational Data Team | UNCLASSIFIED | MAR 2026
USAREUR-AF OD TEAM
PHASE
ACTION
DECISION / OWNER
SUCCESS STANDARD
1 COMMAND AUTHORITY
Issue training directive (EXORD or policy memo) designating Maven Builder Training as required for identified MOSs/roles.
CDR decision: mandatory vs. encouraged by role. G3/J3 staff action.
Signed directive published to all subordinate units.
2 CADRE STANDUP
Identify and assign 5 cadre: 1 OIC + 4 SMEs covering TM-10/20/30/40 tracks. Develop cadre SOP and instructor certification standard.
G6/G2/S6 nominations. OIC appointed by CDR.
Cadre certified; SOP signed; instructors completed TM-40 series.
3 AUDIENCE SEQUENCING
Phase training: TM-10 (all staff) → TM-20/30 (data-adjacent billets) → TM-40 series (specialists by MOS).
G3 decision: phased by echelon or MOS priority. Unit S3s build into ATP.
100% TM-10 completion; TM-40 track assignments published.
4 RESOURCE & ACCESS
Provision Foundry seats, schedule lab time/VTC blocks, integrate into unit training calendars. Coordinate with G6 for network access.
G6 action: license provisioning. G3: calendar deconfliction.
All students have Foundry access NLT training start date.
5 TRACK & REPORT
Establish completion tracking in DTMS/ATRRS. Set Go/No-Go checkpoints per MTP. Report completion status at monthly CDR training brief.
G1/S1 action: reporting format. CDR sets completion deadline (recommended D+180).
Monthly completion report to CDR; Go/No-Go recorded per student.
6 FEEDBACK & SUSTAIN
Conduct AAR after first cohort; update curriculum and cadre SOP quarterly. Integrate into new-hire onboarding and unit OPORDs.
Cadre OIC owns curriculum updates. CDR approves policy changes.
Quarterly AAR complete; curriculum version controlled; onboarding updated.
RECOMMENDED TIMELINE: Directive signed NLT D+30 | Cadre designated D+45 | First cohort begins D+90 | Full force completion D+180
UNCLASSIFIED