## Slide 1: DATA PROGRAM MANAGER ESSENTIALS TM-40J · Specialist Track · Prereq: TM-30
UNCLASSIFIED
UNCLASSIFIED
UNCLASSIFIED
USAREUR-AF · C2DAO · MSS

## Slide 2
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
THE TECHNICAL PM ROLE IN THE MSS ECOSYSTEM
▪ The TM-40J PM translates between technical teams and operational stakeholders
What Technical PMs Do
– Scope and sequence data/AI projects from requirement to production
– Manage backlogs, sprints, dependencies, risks, and delivery timelines
– Build visibility: commander-facing dashboards and project tracking on MSS
What Technical PMs Do NOT Do
– Do not make technical architecture decisions (that is TM-40L/H/I)
– Do not interpret analytical outputs (that is ORSA/analyst function)
– Do not approve models for production (commander retains risk authority)
PM Authority vs. Technical Authority
– PM owns schedule, scope, and stakeholder communication
– Technical lead owns design decisions within approved constraints
– Conflict resolution: PM escalates scope disputes; tech lead escalates design disputes
Curriculum Position: TM-40J after TM-30; advanced track is TM-50J

## Slide 3
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
AGILE FOR DATA AND AI PROJECTS (CHAPTER 2)
Why Agile — Not Waterfall — for Data Projects
– Data requirements are discovered, not specified upfront
– Model performance is unknown until training; iteration is essential
– Operational feedback loops require frequent delivery, not big-bang releases
Scrum Framework for MSS Projects
– Sprint: 2-week default; daily standup; sprint review with stakeholder
– Backlog groomed weekly; stories estimated in story points
– Definition of Done enforced before any story is accepted
Kanban for Operational Support
– Board structure: Backlog → In Progress → Review → Done
– WIP limits prevent overloading the team during high-tempo periods
Sprint Ceremonies: Planning, Standup, Review, Retrospective
– Review: demo working software/data product — no slide decks as proof of work
– Retrospective: identify one improvement per sprint, not a complaint session

## Slide 4
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
ML/AI PROJECT LIFECYCLE (CHAPTER 3)
▪ The ML/AI project lifecycle has six phases — PM has specific actions in each:
Phase 1 — Problem Definition
– PM translates commander's question into a machine-learnable problem statement
– Success criteria defined in measurable terms before development begins
Phase 2 — Data Audit
– PM coordinates access; data engineers assess quality and availability
– PM documents risk if data is insufficient — does not proceed without acknowledgment
Phase 3 — Prototype
– PM scopes the prototype (not full production); time-boxes to 2–3 sprints
Phase 4 — Evaluation
– PM chairs evaluation review; ensures non-technical stakeholders understand output
Phase 5 — Production
– PM coordinates Model Card completion, governance gates, deployment approval
Phase 6 — Sustainment
– PM owns monitoring cadence; escalates model performance degradation

## Slide 5
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
STAKEHOLDER MANAGEMENT AND REQUIREMENTS (CHAPTER 4)
The Translation Problem
– Commanders ask questions; ML Engineers build models; PM bridges the gap
– 'We need better readiness forecasting' ≠ a model specification
– PM extracts: What decision will this inform? What timeframe? What accuracy?
Requirements Elicitation
– Structured interviews: ask for examples of decisions, not feature lists
– Document as user stories: 'As a [role], I need [output] so that [decision]'
Managing Expectations
– Communicate velocity honestly — resist pressure to commit to unrealistic dates
– 'Ready in 2 sprints' is a forecast, not a guarantee; qualify uncertainty
Cross-Track Coordination
– PM maintains dependency log across TM-40H (AI), TM-40I (ML), TM-40L (SWE)
– Blocked dependencies escalated to PM — not resolved ad hoc by engineers
Protecting the Team: PM absorbs stakeholder pressure; engineers execute

## Slide 6
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
PROJECT TRACKING SYSTEMS ON MSS (CHAPTER 5)
Why Track on MSS — Not Spreadsheets
– Single source of truth: same platform as delivery artifacts
– Stakeholder visibility without meetings: dashboard replaces status briefs
– Audit trail: all changes timestamped and attributed
Sprint Board in Workshop
– Object Types: Epic, Story, Task, Blocker
– Link Types: Story-to-Epic, Task-to-Story, Blocker-to-Story
– Views: Sprint Board (Kanban), Backlog (table), Burndown (chart)
Commander-Facing Dashboard
– One page: status by project, milestones hit/missed, blockers, risk flag
– No jargon: 'Green/Amber/Red' with plain-language description
– Design principle: GO/SES reads in 90 seconds — not a data dump
Automated Status Alerts
– AIP-driven alerts when story count drops or blockers age past threshold

## Slide 7
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
RISK AND DEPENDENCY MANAGEMENT (CHAPTER 6)
Risk Types Specific to Data Products
– Data quality risk: source data is incomplete, stale, or inconsistent
– Model risk: model performs in training but fails on operational data
– Infrastructure risk: compute, storage, or access not available when needed
– Governance risk: model card not completed; commander approval not obtained
– Personnel risk: key technical staff rotate before knowledge transfer
Risk Register in MSS
– Risk object: description, probability, impact, mitigation, owner, due date
– Sprint risk review: PM reviews risk register every sprint
– Severity matrix: probability × impact → Red/Amber/Green
Dependency Management
– Common patterns: data pipeline must complete before feature store update
– Model training depends on feature engineering completion
– Deployment depends on governance gate approval
Technical Debt: track as a risk; allocate 20% of sprint capacity to debt reduction

## Slide 8
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
DELIVERY PLANNING AND PRODUCTION READINESS (CHAPTER 7)
Scope / Timeline / Quality Tradeoffs
– PM manages the tradeoff triangle — cannot optimize all three simultaneously
– Default position: do not cut quality; adjust scope or timeline
Definition of Done — Data Product
– Code reviewed and merged; tests passing; documentation current
– Monitoring configured; on-call procedure documented; stakeholder accepted
What 'Production Ready' Means for a Data Product
– Model Card signed; all six governance gates passed
– Rollback procedure tested; drift detection active
– User guide published; training delivered to operational consumers
Milestone Types
– Internal: sprint demo, evaluation complete, staging deployment
– External: commander review, governance gate, production deployment
Post-Release Review: PM chairs at T+14 — measures adoption, not just delivery

## Slide 9
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
CHANGE MANAGEMENT AND USER ADOPTION (CHAPTER 8)
Why Operational Users Resist New Data Products
– Not laziness — trained to distrust unfamiliar data sources
– Legacy tool habits are deeply embedded (AFATDS, GCSS-Army, Excel)
– Fear: wrong model output leads to bad operational decision
Change Management Planning
– Stakeholder map: identify champions, skeptics, and blockers by name
– Champion first: get one influential user to adopt and endorse
– Train-the-trainer: embed capability with unit S6 or data champion
Managing Resistance at Rollout
– Low adoption at T+14: diagnose cause before adding features
– Common cause: product answers the wrong question — go back to requirements
Platform Governance — PM Perspective
– PM participates in C2DAO governance reviews for own products
– Data product retirement: PM owns decommission plan and user notification

## Slide 10
DATA PROGRAM MANAGER ESSENTIALS · TM-40J · Specialist
UNCLASSIFIED
UNCLASSIFIED
TM-40J CURRICULUM OVERVIEW AND NEXT STEPS
TM-40J Chapter Structure
– Ch 1: Technical PM Role and Scope
– Ch 2: Agile Project Management (Scrum/Kanban for data projects)
– Ch 3: ML/AI Project Lifecycle (six phases)
– Ch 4: Stakeholder Management and Requirements Translation
– Ch 5: Project Tracking Systems on MSS
– Ch 6: Risk and Dependency Management
– Ch 7: Delivery Planning and Production Readiness
– Ch 8: Change Management and User Adoption
Appendices
– Project Kickoff Checklist
– Definition of Done — Data Product Standards
– Glossary
TM-40J is the only management-track specialist publication
– Cross-track coordination: works with TM-40G, H, I, K, L daily
Next Steps: Complete TM-40J → eligible for TM-50J (Advanced Program Manager)