## Slide 1: ADVANCED PROGRAM MANAGEMENT TM-50J · Advanced Specialist · Prereq: TM-40J
UNCLASSIFIED
UNCLASSIFIED
UNCLASSIFIED
USAREUR-AF · C2DAO · MSS

## Slide 2
ADVANCED PROGRAM MANAGEMENT · TM-50J · Advanced Specialist
UNCLASSIFIED
UNCLASSIFIED
FROM TM-40J TO TM-50J — SCOPE CHANGE
TM-40J (PM): Manage one data/AI project team
TM-50J (Advanced PM): Manage a portfolio of concurrent data/AI programs
– Multiple teams, multiple dependencies, theater-level visibility
– GO/SES-facing reporting; scaled Agile across teams
– Vendor management (Palantir), contractor management, budget stewardship
The TM-50J PM Profile
– Works at Division/Corps/Theater level — not BCT-level
– Manages program managers, not just engineers
– Serves as primary interface between technical program and senior leadership

## Slide 3
ADVANCED PROGRAM MANAGEMENT · TM-50J · Advanced Specialist
UNCLASSIFIED
UNCLASSIFIED
SCALED AGILE — MANAGING MULTIPLE CONCURRENT TEAMS (CHAPTER 2)
From Project to Program
– Project: one team, one product, one PM
– Program: multiple teams, shared dependencies, portfolio PM
Program Increment (PI) Planning
– Quarterly planning event: all teams define objectives and identify dependencies
– PI objectives reviewed by senior leader before sprint execution begins
– Risk escalation: blockers that cross team boundaries escalated in PI planning
Managing Dependencies Across Teams
– Dependency log maintained in MSS — not in each team's backlog
– Dependency review: weekly at program level, not ad hoc between engineers
Conflict Resolution Between Teams
– Shared resource conflicts escalated to PM — not resolved engineer-to-engineer
– PM arbitrates based on portfolio priority, not loudest voice

## Slide 4
ADVANCED PROGRAM MANAGEMENT · TM-50J · Advanced Specialist
UNCLASSIFIED
UNCLASSIFIED
PORTFOLIO-LEVEL TRACKING AND THEATER VISIBILITY (CHAPTER 3)
Why Portfolio Tracking at TM-50J Level
– Theater commander needs: what is working, what is not, what is at risk
– Not sprint velocity — strategic delivery against mission requirements
Program Tracking Ontology Design
– Object Types: Program, Team, Milestone, Risk, Dependency, Resource
– Link Types: Team-to-Program, Milestone-to-Program, Risk-to-Program
Designing for GO/SES Readability
– One-page portfolio view: program status, milestone health, risk heatmap
– Traffic light status with one-line description — no jargon
– Data quality: stale status worse than no status — enforce update cadence
Program Review Briefing Package
– Three slides: what we planned, what we delivered, what is at risk next quarter
– Attach supporting data in MSS — brief talks to the dashboard, not to slides

## Slide 5
ADVANCED PROGRAM MANAGEMENT · TM-50J · Advanced Specialist
UNCLASSIFIED
UNCLASSIFIED
STAKEHOLDER MANAGEMENT AND DATA CULTURE (CHAPTER 4)
Managing Up: Briefing GO/SES Leadership
– Bottom Line Up Front — always
– Anticipate questions: prepare backup slides for likely concerns
– Uncertainty communication: 'This forecast has ±15% confidence' not 'it depends'
Building Organizational Buy-In for Data Culture Change
– Champion strategy: identify early adopters in each directorate
– Demonstrate value before expecting behavior change
– 'Show me on MSS' replaces 'send me a spreadsheet'
Navigating Command Climate
– Some commanders resist data-driven decision-making — manage the narrative
– Vignette: Commander wants a specific number, not a range — PM must not fabricate precision
Stakeholder Mapping at Program Level
– Power/interest matrix: who can block the program vs. who is just informed

## Slide 6
ADVANCED PROGRAM MANAGEMENT · TM-50J · Advanced Specialist
UNCLASSIFIED
UNCLASSIFIED
QUANTITATIVE DELIVERY MANAGEMENT (CHAPTER 5)
Core Delivery Metrics at Program Level
– Velocity trend (not snapshot): is the team accelerating or decelerating?
– Predictability: % of sprint commitments delivered as planned
– Dependency resolution rate: how quickly are cross-team blockers resolved?
– Cycle time: idea to production — the true delivery clock
Interpreting Metrics Correctly
– Velocity drop: diagnose before reacting — could be planned debt reduction
– High predictability + low velocity: team is sandbagging estimates
– Low predictability + high velocity: team is overcommitting
Program-Level Predictability Targets
– 70% of PI objectives delivered as committed — Army standard for mature programs
Communicating Metrics to Leadership
– Metrics tell a story — PM frames the story, not the data analyst
– Never present metrics without interpretation and recommended action

## Slide 7
ADVANCED PROGRAM MANAGEMENT · TM-50J · Advanced Specialist
UNCLASSIFIED
UNCLASSIFIED
VENDOR AND CONTRACTOR MANAGEMENT (CHAPTER 7)
The Palantir Partnership Model
– Palantir FDEs: technical resources embedded with the MSS program
– FDE scope: technical implementation only — not requirements definition
– PM owns requirements; Palantir implements; government retains decision authority
Task Order Management
– TM-50J PM manages task order scope, deliverables, and acceptance criteria
– Change requests to task order go through PM — not direct FDE-to-user negotiation
Managing Palantir Relationship Day-to-Day
– Weekly sync: FDE lead + PM — scope, blockers, velocity
– Do not allow FDEs to independently prioritize backlog — PM owns priority
Vendor Performance Documentation
– Delivery log: what was committed vs. delivered, by sprint
– Performance documentation supports future contract negotiations

## Slide 8
ADVANCED PROGRAM MANAGEMENT · TM-50J · Advanced Specialist
UNCLASSIFIED
UNCLASSIFIED
TEAM DESIGN, GOVERNANCE, AND PROGRAM LEADERSHIP (CHAPTERS 8–9)
Designing the Data Program Team Structure
– Stream-aligned teams: one team per bounded capability domain
– Platform team: shared infrastructure supporting stream teams
– Enabling team: governance, standards, security — support function, not gatekeeper
Skill Mix Planning and Personnel Turbulence
– At Army rotation rates, the program loses key personnel every 12–18 months
– Cross-training and documentation are not optional — they are succession planning
Program Governance Framework
– Decision Authority Matrix: who approves what — documented, not implied
– Change control for production systems: all changes go through PM approval
Program Communication Architecture
– Weekly: team syncs, dependency review
– Monthly: program review with senior stakeholder
– Quarterly: PI planning with full leadership attendance
Writing the Program SITREP: status + forecast + risk + ask